## Slide 1: Pre-Project Scope of Work Long term & Medium term plan, Timeline, Required sources, Profile
KEK リニアコライダー計画推進室
宮 原 正 信
17. Apr 2014
CFS near term & Required ADI input 6-12 month activities, required ADI information
CFS-ADI Joint Meeting から

## Slide 2
Topographical Survey
Environmental Assessment
Geological Survey
Basic Planning
1 annual |  | 2 annual |  | 3 annual |  | 4 annual |  | 5 annual | 
Estimation
Basic Design
Detailed Design
Contract
Construction Phase
Predesign Phase
Design Phase
Contract Phase
LCC Review
Basic Plan Report
Basic Design Document
Detailed Design Document
Contract Document
LCC Review
Investigation in the Design Phase
Pre Construction Schedule
Long term & Medium term
LCC Review
地形測量
地質調査
環境アセス

## Slide 3
Basic Planning
1 annual |  | 2 annual |  | 3 annual |  | 4 annual |  | 5 annual | 
Estimation
Basic Design
Detailed Design
Contract
Construction Phase
Predesign Phase
Design Phase
Contract Phase
Basic Plan Document
Basic Design Document
Detailed Design Document
Contract Document
Pre Construction Design Work
Design Phase Skeleton
基本計画
基本設計
実施設計
施設設計に備えて、 ﾌﾟﾛｼﾞｪｸﾄの基本構想や施設の全体計画、基本仕様等をまとめた文書(事業計画書)
実施設計のために、各計画施設の基本形状や基本寸法等の基本仕様を明示した設計図書
契約や施工のために計画施設の形状寸法や構造・材料・工法等の詳細仕様を明示した設計（契約）図書
基本計画書
基本設計書
実施設計書

## Slide 4
PAn investigation plan in every phase
Investigation Plan
Investigation Required by each phase |  |  | 
 | Basic Planning | Basic Design | Detailed Design
Topographical Investigation | Preparation | Basic Survey | Additional Survey
 | Collection of the exiting Data & Materials - 1/10,000 map | Creating a topographical map in the ground site - 1/500~1/1,000 | Optional Survey: - Construction site - Temporary site
Geological Investigation | Preliminary Survey | Basic Survey | Additional Survey
 | Necessary Survey: - Boring: 1(near DH) - Seismic wave Survey (1 km, near DH ) | Necessary Survey: - Borehole investigation: 4(near DH) & 6 (near AH) - Seismic wave Survey: (1,000m×5, near A/P) | Optional Survey: - 10 Boreholes(?) - Unknown place of geological conditions Design problem part
Environment Impact Assessment | Preparation | Environmental assessment survey | 
 | - Draft plan for Field Investigation - Literature Research | - Field Investigation(1) - Making the Submitted document | - Field Investigation(2) - Creating an Evaluation document
地形測量
地質調査
環境ｱｾｽ

## Slide 5
PAn investigation plan in every phase
Investigation Plan
Investigation Required by each phase |  |  | 
 | Basic Planning | Basic Design | Detailed Design
Topographical Investigation | Preparation | Basic Survey | Additional Survey
 | Collection of the exiting Data & Materials - 1/10,000 map | Creating a topographical map in the ground site - 1/500~1/1,000 | Optional Survey: - Construction site - Temporary site
Geological Investigation | Preliminary Survey | Basic Survey | Additional Survey
 | Necessary Survey: - Boring: 1(near DH) - Seismic wave Survey (1 km, near DH ) | Necessary Survey: - Borehole investigation: 4(near DH) & 6 (near AH) - Seismic wave Survey: (1,000m×5, near A/P) | Optional Survey: - 10 Boreholes(?) - Unknown place of geological conditions Design problem part
Environment Impact Assessment | Preparation | Environmental assessment survey | 
 | - Draft plan for Field Investigation - Literature Research | - Field Investigation(1) - Making the Submitted document | - Field Investigation(2) - Creating an Evaluation document
地形測量
地質調査
環境ｱｾｽ

## Slide 6
Proposal from JSCE／ILC sub-committee
Guidlines for the Civil Engineering
Work of ILC Facilities
PAn investigation plan in every phase
Geological Investigation
5 Sectional Meetings
■ Project Investigation
■ Large Cavern
■ Horizontal Tunnel
■ Special Tunnel
■ Disaster Prevention
3. Apr 2014
ＩＬＣ地下構造物の設計・施工ガイドライン

## Slide 7
PAn investigation plan in every phase
Geological Investigation
Proposal from JSCE in the Guidline (3)
  Important place of Investigation
    Boundary zone with different rock kind (fracture zone, Weathering zone, etc.)
    Place of the Topography changes such as a Valley part and the river-bed part
    Important place for the performance and function of the accelerator facility
BDS, DR, DH
Hitokabe Granite
Senmaya Granite
Orikabe Granite
過不足なく！ 重要箇所を！

## Slide 8
□ Profiles of Geological Surveys along the project
Borehole Survey
Seismic Exploration Survey
Profile of Electromagnetic Survey
Hitokabe Granite
Senmaya Granite
Orikabe Granite
 | Basic Planning | Schematic Design | Detailed Design
Borehole Survey | - 1 p DH area | - 5 p DH/DR area | - 10 p along the BL
Seismic Exploration | - 1 area /1,000m | - 5 area /5,000m | 0 (Additional)
New IR point?
Geological Survey at pre-construction stage
PAn investigation plan in every phase
Geological Investigation
Survey area: @Bedrock boundary, Riverbed part
Riverbed part
各フェーズ毎に ｽﾃｯﾌﾟ ﾊﾞｲ ｽﾃｯﾌﾟで！

## Slide 9
Environmental Assessment -Ⅰ
System of Environmental assessment
    Environmental impact assessment by Law
    targeted to large-scale development projects.
    (Dam, Road, Railroad, etc.)
    Environmental Impact Assessment by Ordinace (Prefecture)
    targeted to projects not covered in the national system.
    An enterprise cannot be started until it submits an evaluation document.
  Application to the ILC project
    Environmental impact assessment law
    Environmental Impact Assessment Ordinance
    Not applicable (IWATE & MIYAGI pref.)
The pilot survey of the Raptores
Field survey takes time most is on going.
法ｱｾｽ
条例ｱｾｽ

## Slide 10
Environmental Assessment –Ⅱ
  Voluntary Assessment
    We should do perform the Assessment strategically (SEA)
Air Environment | Air quality
 | Noise
 | Vibration
 | Stench
Water environment | Dirt of water
 | Water turbidity
 | Groundwater
Landscape | 
Other environmental | Geology
 | Noise
 | Foundation
 | Soil
Animal | 
plant | 
Waste | 
Greenhouse gas | 
Strategic Environment impact assessment
Main Survey Item in Environmental assessment
Rare Creature:
Raptores Survey
Northern goshawk
Golden eagle
戦略ｱｾｽ
猛禽類調査
自主ｱｾｽ

## Slide 11
Environmental assessment –Ⅴ
Standard schedule based on the local govinmment regulation
 | 1 anual |  |  |  |  |  | 2 anual |  |  |  |  |  | 3 annual |  |  |  |  |  | Procedure | Work | Work
Making a Method Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3.0 | 
Inspection Method Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.0 |  | 
Resident opinion submitting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.5 |  | 
Create a opinion summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.5 | 
Governor opinion submitting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3.0 |  | Max4.0
Field investigation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12.0 | 
Submission of preparations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4.0 | 
Inspection the preparations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.0 |  | 
Resident opinion submitting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.5 |  | 
Opinion summary submitting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.5 | 
Governor opinion submitting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4.0 |  | Max5.0
Creation of the Evaluation Doc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3.0 | 
Inspection the evaluation Doc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.0 |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 11.0 | 25.0 | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 36.0 |  | 
Key Factors :
Inspection,
Briefing,
Hearing the opinion
Field Survey
■ Assessment process generally takes ３ years.
Scoping
Case of Iwate Prefecture
■ Pilot Survey is on going by local government !
The Raptores investigation which a field survey takes time most
公告・縦覧
意見聴取
説明会

## Slide 12
Topographical Survey
Environmental Impact Assessment
Geological Survey
Basic Planning
1 annual |  | 2 annual |  | 3 annual |  | 4 annual |  | 5 annual | 
Estimation
Basic Design
Detailed Design
Contract
Construction Phase
Predesign Phase
Design Phase
Contract Phase
LCC Review
Basic Plan Report
Basic Design Document
Detailed Design Document
Contract Document
LCC Review
Investigation in the Design Phase
Pre Construction Schedule
Long term & Medium term
LCC Review

## Slide 13
Pre Construction Work Scope
 | Underground Facilities |  |  |  | 
Work | ML | AH | DR | BDS | DH
Facility Arrangement | B/C | B/C | C | C | B/C
Basic Shape, Dimension | B/C | B/C | B/C | C | B/C
Civil/Architectural Design | C | C | C | C/D | C
Electronic Design | C | C | C | C/D | C
Mechanical Design | C | C | C | C/D | C
Surface Facilities |  | 
AY | CS | CC
D | C | D
D | C | D
D | C | D
D | C | D
D | C | D
Current Status: Facility Planning Progress
 | Requirement | Technical Study
A | Clear | Completed
B | Clear less | Under study
C | Unclear partially | Partially executed
D | Unclear | Not yet started
Legend: Progress degree
 | Technical Study
AH | Access Hall
AY | Access Yard
CS | Central Substation
CC | Central Campus
Legend: Facility

## Slide 14
Near Term Activities : 1
１ | Decision of Facility arrangement
■ Determination: IR Point & Access way
Revision the DH Configuration (TDR)
Access Facility to DH (VS or HT)
Underground Facilities Layout and configuration
■ Determination: Surface Facility Layout
Surface Facilities planning (Assembly hall)
Kick off some kind of Investigation
(Topographical survey, Environmental Assessment)
Consultation with regional society
In Basic planning stage

## Slide 15
2 | Decision of Facility arrangement
■ Determination: Beam line level (elevation)
■ Determination: BL Route and Length
In Basic planning stage
Revision the Access Point (AH & AT portal)
Access Facility to ML (AT length & location)
Consistency with surface environment
Vibration Impact Evaluation
(Artificial, Separation from Riverbed)
Access Facility to ML (AT length & location
Groundwater treatment (Natural Drainage system)
Near Term Activities : 2

## Slide 16
3 | Decision of the basic facilities plan
■ Specific study of Power equipment
(Central power receiving facility)
In Basic planning term
Location of the Central Power Station
Power voltage, power receiving system
Consultation of Power receiving line
Negotiation with local power company
Planning the emergency power system
Near Term Activities : 3

## Slide 17
Planning
1 annual |  | 2 annual |  | 3 annual |  | 4 annual |  | 5 annual | 
Additional Survey
Basic Survey
Detailed Survey
Bidding
Topographic Document
Geological Document
Assessment Statement
Preliminary
survey
Environmental Impact Assessment Survey
Preliminary
Survey
Basic Design
Detailed Design
Contract
Construction Phase
Predesign phase
Design phase
Contract phase
Geological Survey
Environmental Impact Assessment
Topographical Survey
Basic survey(1)
Review
Review
Review
Basic survey(2)
Pre Construction Schedule
Long term & Medium term
  <Survey for land Acquisition>

## Slide 18
Summary：CFS-ADI Joint Meeting
□ 基本計画段階で決定すべき課題抽出（1年以内）
1. Ｄetector Hall：IP、アクセス方式の見直し
2. ビームライン：ルート、高さ（標高レベル）
3. トンネル長さ、レイアウト（ＢＤＳ/Positron Source）
□ 基本設計に向けた喫緊の課題（CFS）
1. 設計に必要な最小限の経費算定（調査・設計）
2. ＴＤＲ見直しに伴うスケジュール・コストの再検討
3. 基本計画確定のためのＡＤＩへのRequirement集約
4. 基本計画書（案）の策定→ＬＣＣへの提示、レビュー